## Project Planner
Nutra Graph
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS | [5 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Initalisation
1.1 Define Project Overview (PP:1) | 1 | 1 | 4 | 1 | 100%
1.2 Assign Project Manager | 1 | 1 | 2 | 1 | 100%
1.3 Assign Team Roles | 1 | 1 | 2 | 1 | 100%
1.4 Define Stakeholders (PP:1.2) | 1 | 1 | 4 | 1 | 100%
1.5 Define Project Scope (PP:1.3) | 1 | 1 | 4 | 2 | 100%
2. Planning
2.1 Create Project Plan (PP:1-4) | 2 | 1 | 4 | 3 | 100%
2.2 Activity Definition Estimation (PP:3) | 2 | 1 | 4 | 1 | 100%
2.3 Create WBS (PP:2) | 3 | 1 | 5 | 1 | 100%
2.4 Create Gant Chart (PP:4) | 3 | 1 | 5 | 2 | 100%
3. Design
3.1 Define System Vision (SD:1) | 4 | 1 | 4 | 1 | 100%
3.2 Define User Requirments (SD:2) | 4 | 1 | 5 | 1 | 100%
3.3 Define Software Requirments (SD:2.2) | 4 | 1 | 5 | 1 | 100%
3.4 Use Case's + Diagram (SD:2.3-2.4) | 5 | 1 | 5 | 2 | 100%
3.5 Software Design & Components (SD:3) | 5 | 1 |  |  | 0%
3.6 Structrual Design (SD:4.1) | 6 | 1 |  |  | 0%
3.7 Detailed Design (SD:3.2.3) | 6 | 1 |  |  | 0%
3.8 Wireframe Design (SD:4.2) | 7 | 1 | 5 | 1 | 100%
4. Software Development
4.2 GUI Development | 8 | 7 |  |  | 0%
4.3 Data Base Intergration | 15 | 6 |  |  | 0%
4.4 Database Algorithm | 21 | 6 |  |  | 0%
4.5 Pie & Bar Graph Intergration | 27 | 3 |  |  | 0%
5. Testing & QA
5.1 Intergration Testin | 30 | 1 |  |  | 0%
5.2 User Acceptance Testing | 31 | 1 |  |  | 0%
5.3 Bug Fixes | 32 | 3 |  |  | 0%
6. Deployment
6.1 Document Handover | 35 | 1 |  |  | 0%
6.2 Software Deployment | 35 | 1 |  |  | 0%